## Sheet1
			Assignment	Estimated Time (hours)	Actual Time (hours)
1. Chatbot
	1.1. Initial Meeting		All	1	1		note: times to nearest 1/2 hr
		1.1.1 Define Project Theme	'’
		1.1.2. Project Management Roles	'’
		1.1.3 Logical Brainstoriming	'’

	1.2. Evaluate PM
		1.2.1. Review Roles	All
		1.2.2. Project Description	Alex	1	1
		1.2.3. SDLC Rationality	Nick	1	1
		1.2.4. WBDS	Quinn	0.5	0.5
		1.2.5. Gantt Chart	Paige	1	1
		1.2.6. Close out PM Review	All
	1.3. Design
		1.3.1. Review Project Requirements	All	0.5	0.5
		1.3.2. Create Class Logic	Quinn	1
		1.3.3. Implement Basic Architechure	Quinn	1
	1.4. Functional Implementation		Quinn	0.5	2
			Alex	0.5	1
			Paige	0.5	0.5
			Nick	0.5	0.5

	1.5. Testing
		1.5.1. Limitation Analyis	Quinn	0.5	0.5
		1.5.2. Stress-Test Dialogue	Quinn	0.5	0.5
		1.5.3. Complete 30-line run	Quinn	0.5	0.5
	1.6. Final Review
		1.6.1. Review Documentation Quality	Paige	0.5	0.5